## Risk_Register
Risk Register for Super Shipper Sytem
Prepared by: |  |  | HuyTDH |  |  | Date: | 2015-09-16
Last Updated by: |  |  | HuyTDH |  |  | Date: | 2015-09-20
No | Rank | Risk | Description | Category | Root Cause | Triggers | Probability | Impact | Avoidance plan | Contingency plan | Fallback plan | Risk owner | Status
R1 | 3 | Lack of team member | The number of members decreases and not enough for work | People | Member out team | Dissatisfied with other members, have unexpected trouble | Low | High | PM need to have a meeting with this member and suggest him/her still be there. | Resolve the problems inside team. For example: PM has some methods to motivate members | reduce scope | HoangLVQ | Not yet active
R2 | 1 | Conflict among team members | Team member disagree with others and refuse to work or work below their ability | People | Unclear requirement specification. Team members do not unify on solutions | Has issue inside team | Medium | High | Plan some team building to improve teammate | Have a meeting to solve conflict problem | Team create meeting to secret vote for choices | HuyTDH | Activated / Solved
R3 | 2 | Lack of skill and knowledge for a specified work | Team member don't have enough skill, knowledge to do their task. Example: can't control new technologies in project | People | Member don't have enough time to learn/improve needed skills | Member inform that they don't know how to do. | Medium | High | Have detail training plan. All members must know what skills and what kinds of knowledge they must have. | Team members help each other improve skill and ability | Working over time | HoangNK | Activated / Solved
R4 | 4 | Requirement change | The scope may change, some requirements may be added | Requirement | SRS not good (not realistic, not feasibility, not meet customer needs) | Project team cannot develop the system as description in SRS. | High | Medium | Requirement should be paid a lot of attention. SRS should be peer reviewed, reviewed carefully by PM and the supervisor. | With each requirement changes, the project team should have a meeting to analysis the change requests and take actions. | Re-estimate and update plan. | HoangLVQ | Not yet active
R5 | 5 | Team member distraction | Team members don't pay enough time for working in the project, productivity is low | People | Undisciplined and habit of team member, loose management | Team members does not spend time for work and tasks are not completed on time | Medium | Medium | Setting rule and minus of do not meet the deadline: punish money and named at meeting minute. | Punish the member do not meet the deadline. | Working over time | HoangLVQ | Activated / Solved
R6 | 7 | Inability to verify/validate products with requirements. | Can't verify/validate the deliverable products whether meet the requirements or not | Process | Problem in product quality control | Inability to verify/validate products against requirements. | Medium | Low | Create detail testing plan. Research to find out suitable test method | Print out the result to check by eyes. Debug into code to see how the code is running | Ask for help from supervisors | NhungNTH | Not yet active
R7 | 6 | Can’t commit work because internet connection | Internet connection is down and team members can't submit work, merge code, ... | Technology | Can’t connect to the git repository server | Internet connection is down | Low | Medium | Have a backup local repository | Manage resource via local repository while can't connect to the internet one. | Copy resource by using USB | HuyTDH | Not yet active
R8 | 8 | Product doesn’t meet requirement | Some functions doesn't satisfy the requirement in SRS | Process | Team member not understand requirement | Function doesn’t meet the requirement | Medium | Low | PTL have to review source code and follow requirement | Fix bugs | Assign other members doing those functions | HoangNK | Not yet active