## Defect Report
DEFECT REPORT
Project Name | <KarryWell> |  | Creator |  | NhungNTH
Project Code | <KW> |  | Reviewer/Approver |  | HoangLVQ
Document Code |  |  | Issue Date |  | 02/09/2015
Notes
No | Module code | Open | Fixed | Closed | Won't Fix | Pending | Number of Bug
1 | Admin | 0 | 0 |  | 0
3 | Store | 0 | 0 |  | 0
4 | Mobile | 0 | 0 |  | 0
5
6
7
8

## Admin
Tab
| Creator |  | NhungNTH
| Total bugs: | 29 | Pending: |  | 0
| Open: | 0 | Won't Fix: |  | 0
| ReOpen: | 0 | Cancel: |  | 0
| Fixed | 0 | Closed: |  | 29
Defect ID | Module | Description | Evidance | Type | Severity | Priority | Assign to | Status | Create by | Created Date | Close Date | Comment
DF01 | Logout | Admin can't logout | Admin_Evidance_DF01 | Coding Logic | Medium | High | HoangNK | Closed | NhungNTH | 2015-11-28 | 2015-12-06
DF02 | View Store List | The about line at the bottom of page: "* The last period balance is the balance of last period from 25/12/1969 to * The current period balance is the balance until now" |  | Coding Logic | Cosmetic | Low | HoangNK | Closed | NhungNTH | 2015-11-28 | 2015-12-06
DF03 | Add shipper | Indentity Card textfield notify the errors twice. "This value length is invalid. It should be between 9 and 9 characters long. This value is required." |  | Coding Logic | Cosmetic | Low | HoangNK | Closed | NhungNTH | 2015-11-28 | 2015-12-06
DF04 | Add shipper | Indentity Card textfield notify an error: "This value length is invalid. It should be between 9 and 9 characters long. " |  | Coding Logic | Cosmetic | Low | HoangNK | Closed | NhungNTH | 2015-11-28 | 2015-12-06
DF05 | Add shipper | DOB textfield is able to add the time of the future. |  | Business Logic | Cosmetic | Low | HoangNK | Closed | NhungNTH | 2015-11-28 | 2015-12-06
DF06 | Add shipper | Phone number textfield can add a number that does not starts by 0. |  | Business Logic | Cosmetic | Low | HoangNK | Closed | NhungNTH | 2015-11-28 | 2015-12-06
DF07 | Add store | Socket can't take location of the store to put into map |  | Coding Logic | Medium | Medium | HoangNK | Closed | NhungNTH | 2015-11-28 | 2015-12-06
DF08 | View Shipper List | Automatically quit out from system when click button "Edit" in Option column. |  | Coding Logic | Medium | High | HoangNK | Closed | NhungNTH | 2015-11-28 | 2015-12-06
DF09 | View shipper Profile | unable to test |  | Coding Logic | Medium | Medium | HoangNK | Closed | NhungNTH | 2015-11-28 | 2015-12-06
DF10 | Search Shipper | Can't search when the selected type is "ShipperID" |  | Coding Logic | Cosmetic | Low | HoangNK | Closed | NhungNTH | 2015-11-28 | 2015-12-06
DF11 | Notify | Don't need to notify to store when the shippers changes their status . |  | Business Logic | Medium | Medium | HoangNK | Closed | NhungNTH | 2015-11-29 | 2015-12-06
DF12 |  | The location between shipper and store is still perfrom on map while the order was done. |  | Coding Logic | Serious | High | HoangNK | Closed | NhungNTH | 2015-11-29 | 2015-12-06
DF13 | Store detail | Logout when clicks on the store's owner button |  | Feature Missing | Serious | High | HoangNK | Closed | NhungNTH | 2015-11-29 | 2015-12-06
DF14 | Dashboard | "DELIVERY SERVICE TODAY" haven't done yet. |  | Feature Missing | Medium | Medium | HoangNK | Closed | NhungNTH | 2015-11-29 | 2015-12-06
DF15 | Dashboard | The progressbar set 100% |  | Feature Missing | Cosmetic | Low | HoangNK | Closed | NhungNTH | 2015-11-29 | 2015-12-06
DF16 | Dashboard | There is not Breadcrumb |  | Business Logic | Medium | Medium | HoangNK | Closed | NhungNTH | 2015-11-29 | 2015-12-06
DF17 | Add store | ID,Email,Phone doesn’t check "exists condition" |  | Business Logic | Cosmetic | Low | HoangNK | Closed | NhungNTH | 2015-11-29 | 2015-12-06
DF18 | Assign Task | Haven't upated stock when assign task for shipper |  | Coding Logic | Medium | Medium | HoangNK | Closed | NhungNTH | 2015-11-29 | 2015-12-06
DF19 | Add Order | Can't add orders |  | Business Logic | Serious | High | HoangNK | Closed | NhungNTH | 2015-11-29 | 2015-12-06
DF20 | Order Detail | Haven't completed yet. |  | Coding Logic | Serious | High | HoangNK | Closed | NhungNTH | 2015-11-29 | 2015-12-06
DF21 | Dashboard | The tasks in Dashboard / View Task List are not realtime |  | Coding Logic | Medium | High | HoangNK | Closed | NhungNTH | 2015-11-30 | 2015-12-06
DF22 | Issue | Order list page show half of it only. |  | User Interface | Cosmetic | Low | HoangNK | Closed | NhungNTH | 2015-11-30 | 2015-12-06
DF23 | Assign Task | Does not updated data when the shipper changes tasks status. |  | Coding Logic | Medium | Medium | HoangNK | Closed | NhungNTH | 2015-11-30 | 2015-12-06
DF24 | Assign Task | Assign task processing offline for shipper |  | Business Logic | Medium | Medium | HoangNK | Closed | NhungNTH | 2015-11-30 | 2015-12-07
DF25 | Assign Task | "Confirm Dialog" , YES button and Assign button have the same function |  | User Interface | Cosmetic | Low | HoangNK | Closed | NhungNTH | 2015-11-30 | 2015-12-07
DF26 | Assign Task | Does not push the task into the order list when assgin task. |  | Coding Logic | Medium | Medium | HoangNK | Closed | NhungNTH | 2015-11-30 | 2015-12-07
DF27 | Dashboard | "TASK TODAY" contain the failed task. |  | Business Logic | Medium | Medium | HoangNK | Closed | NhungNTH | 2015-11-30 | 2015-12-07
DF28 | Dashboard | Issue Box button incorrect position. |  | Coding Logic | Medium | Medium | HoangNK | Closed | NhungNTH | 2015-11-30 | 2015-12-07
DF29 | Noti | Notify wrong information when the shipper changes their status to order status. |  | Coding Logic | Medium | Medium | HuyTDH | Closed | NhungNTH | 2015-11-30 | 2015-12-07

## Admin_Evidance
DF01
Defect Description
Admin can't logout
Step to perform
|  | Step 1: | Admin login
|  | Step2: | Click "Logout" button
| Actual | Login screen display
| Expected | Admin can't logout from system
DF02
Defect Description
The "About" description at the end of the page
Step to perform
|  | Step 1: | Admin login
Actual
The last period balance is the balance of last period from 05/12/2015 to 07/12/2015
Expected
The last period balance is the balance of last period from 25/12/1969 to
DF05
Defect Description
User can add unreal birthday
Step to perform
|  | Step 1: | Admin login
|  | Step 2: | Clicks "Add shipper" button
Actual
User can add valid birthday
Expected
See image
DF06
Defect Description
User can add unreal phonenumber
Step to perform
|  | Step 1: | Admin login
|  | Step 2: | Clicks "Add shipper" button
Actual
User can add valid phonenumber
Expected
See image

## Store
Tab
| Creator |  | NhungNTH
| Total bugs: | 12 | Pending: |  | 0
| Open: | 0 | Won't Fix: |  | 0
| ReOpen: | 0 | Cancel: |  | 0
| Fixed | 0 | Closed: |  | 12
Defect ID | Module | Description | Evidance | Type | Severity | Priority | Assign to | Status | Create by | Created Date | Close Date | Comment
DF01 | Logout | Can't logout |  | Coding Logic | Medium | High | KhanhKC | Closed | NhungNTH | 2015-11-24 | 2015-12-05
DF02 | Search Order | search : "Pickup Address" but don't have pickup address column in Order list |  | User Interface | Cosmetic | Low | KhanhKC | Closed | NhungNTH | 2015-11-24 | 2015-12-05
DF03 | Make Order | in the second step, total current weight and you can add more had to be calculated before you click add button |  | Business Logic | Cosmetic | Low | KhanhKC | Closed | NhungNTH | 2015-11-24 | 2015-12-05
DF04 | Make Order | in the second step, can fill amount 0 |  | Business Logic | Medium | Medium | KhanhKC | Closed | NhungNTH | 2015-11-24 | 2015-12-05
DF05 | Make Order | Ở step 2, Trong cột description, khi điền chữ không cách bị vỡ khung của bảng |  | User Interface | Cosmetic | Low | KhanhKC | Closed | NhungNTH | 2015-11-24 | 2015-12-05
DF06 | Order Detail | save only 1 address line |  | User Interface | Cosmetic | Low | KhanhKC | Closed | NhungNTH | 2015-11-25 | 2015-12-05
DF07 | Edit Order | while editingg order, save only 13 phone numbers in phone text file add |  | Coding Logic | Medium | Low | KhanhKC | Closed | NhungNTH | 2015-11-25 | 2015-12-05
DF08 | Noti | Clicking noti is not rounted to the correct site reporting |  | Coding Logic | Medium | High | KhanhKC | Closed | NhungNTH | 2015-11-25 | 2015-12-05
DF9 | Dashboard | show the address of the store is missing |  | Coding Logic | Cosmetic | Low | KhanhKC | Closed | NhungNTH | 2015-11-25 | 2015-12-05
DF10 | transaction history | at admin confirm payment , Store doesn't auto - load that transaction |  | Coding Logic | Medium | Medium | KhanhKC | Closed | NhungNTH | 2015-11-25 | 2015-12-05
DF11 | Dashboard | at 'store cancel order ' admin had accepted, the order imformation in order list did not show the status ' cancle' |  | Coding Logic | Medium | Medium | KhanhKC | Closed | NhungNTH | 2015-11-25 | 2015-12-05
DF12 | Dashboard(Done button) | at 'order done' completion date is not update |  | Coding Logic | Medium | Medium | KhanhKC | Closed | NhungNTH | 2015-11-25 | 2015-12-05

## Store__Evidance
DF03
Defect Description
At step 2, total current weight must calculate before clicks "Add" button
Step to perform
|  | Step 1: | Admin login
|  | Step 2: | Clicks "Make an order" button
Actual
Total weight được tính trước khi click "Add" button
Expected
See image
DF4
Defect Description
Amount equal 0
Step to perform
|  | Step 1: | Admin login
|  | Step 2: | Clicks "Make an order" button
Actual
Amount is equal to or greater than 0
Expected
See image

## Mobile
Tab
| Creator |  | NhungNTH
| Total bugs: | 17 | Pending: |  | 0
| Open: | 0 | Won't Fix: |  | 0
| ReOpen: | 0 | Cancel: |  | 0
| Fixed | 0 | Closed: |  | 17
Defect ID | Module | Description | Evidance | Type | Severity | Priority | Assign to | Status | Create by | Created Date | Close Date | Comment
DF01 | Login | login in app as well aslogout succeded, but logion was not |  | Coding Logic | Medium | Medium | QuyenNV | Closed | NhungNTH | 2015-11-26 | 2015-12-04
DF02 | Login | not fill in username or password, app display uncorrect error mess |  | Business Logic | Cosmetic | Low | QuyenNV | Closed | NhungNTH | 2015-11-26 | 2015-12-04
DF03 | Order Detail | displaying lack Pick-up Adress |  | Coding Logic | Cosmetic | Low | HuyTDH | Closed | NhungNTH | 2015-11-26 | 2015-12-04
DF04 | Grap Order | display mess on pop-up with vietnames |  | Business Logic | Cosmetic | Low | QuyenNV | Closed | NhungNTH | 2015-11-26 | 2015-12-04
DF05 | Issue | when sending issue(type not find customers) order delivering in tab express doesn't show on order slected in the issue screen |  | Coding Logic | Cosmetic | High | QuyenNV | Closed | NhungNTH | 2015-11-26 | 2015-12-04
DF06 | Orrder History | time is not |  | Business Logic | Medium | Medium | HuyTDH | Closed | NhungNTH | 2015-11-26 | 2015-12-04
DF08 | Pickup | after pickup, not display date |  | User Interface | Cosmetic | Low | HuyTDH | Closed | NhungNTH | 2015-11-26 | 2015-12-04
DF09 | Task Detail | address doesn't display all of long addresses |  | User Interface | Cosmetic | Low | QuyenNV | Closed | NhungNTH | 2015-11-26 | 2015-12-04
DF10 | Grap Order | Grap Orderhad to click continously to receive order |  | Business Logic | Medium | Medium | HoangLVQ | Closed | NhungNTH | 2015-11-26 | 2015-12-04
DF11 | Task Detail | after had been done, not display delivery address |  | Business Logic | Medium | Medium | HuyTDH | Closed | NhungNTH | 2015-11-26 | 2015-12-04
DF12 | Task Detail | Call Admin doesn't operate in Android |  | Business Logic | Medium | Medium | HuyTDH | Closed | NhungNTH | 2015-11-27 | 2015-12-04
DF13 | Noti | when store cancel order,admin recevied , not mess sending to shipper |  | Business Logic | Medium | Medium |  | Closed | NhungNTH | 2015-11-27 | 2015-12-04
DF15 | Issue | Issue good fail doesn't display order status bring to stock |  | Business Logic | Medium | Medium | QuyenNV | Closed | NhungNTH | 2015-11-27 | 2015-12-04
DF16 | Grap Order | Shipper cancle order,and admin resolved but store grab order was not found |  | Coding Logic | Medium | Medium | HoangLVQ | Closed | NhungNTH | 2015-11-27 | 2015-12-04
DF17 | Task | a shipper is received over 3 active tast in the same time |  | Business Logic | Serious | High | HoangLVQ | Closed | NhungNTH | 2015-11-27 | 2015-12-04
DF18 | Task | Task type is ship. When assign to shipper , shipper actives succeed but not moving to state lacking check code out-stock |  | Coding Logic | Medium | Medium | HuyTDH | Closed | NhungNTH | 2015-11-27 | 2015-12-04
DF19 | Task | tast screen is only recevied the order of find shipper from the store |  | Feature Missing | Serious | High | HuyTDH | Closed | NhungNTH | 2015-11-27 | 2015-12-04

## Mobile_Evidance
DF01
1.Tab on icon App