## Cover
WBS Document
Project Code | JS0702_HST_VH |  |  | Creator | LongNB, TuyenPT, DuongQT
Document Code | JS0702_HTS_WBS_Vietnamese_Handbook |  |  | Reviewer/Approver | Dat.QT
Purpose | This doc was created to give a clear view about all work need to be done in the project
Doc Name | Description |  |  |  | Note
WBS | List all works in a break down structure
WBS Dictionary | Define more detail for each works in WBS above
Record Of Change
Effective Date | Version | Change Item | *A,D,M | Change description
2015-01-29 | 1.0 | All | A | Add New

## WBS
Work Breakdown Structure |  | Created by | LongNB
|  | Reviewed by | DatQT
No. | Tasks
1 | Initiate Project
1.1 | Kick-off Meeting
1.2 | Study necessary technique
1.3 | Study feasibility
1.4 | Create report
2 | Project Plan Phase
2.1 | Setup Project Environment
2.1.1 | Prepare Hardware
2.1.2 | Setup develop tools
2.2 | Develop Project Schedule
2.2.1 | Build WBS
2.2.2 | Define project Estimate
2.2.3 | Define project Schedule plan
3 | Software Requirement Phase
3.1 | User requirement specification
3.2 | System requirement specification
3.3 | Entity relationship diagram and data structure
4 | Design Description Phase
4.1 | System Achitecture Design
4.2 | Component Diagram
4.3 | Sequence Diagram
4.4 | User Interface Design
4.5 | Database Design and Data structure
5 | Implement Phase
5.1 | Build Data
5.1.1 | Build sentence
5.1.2 | Build sound file
5.2 | Coding
5.2.1 | Conversation
5.2.2 | Favorite
5.2.3 | History
5.2.4 | Search
5.2.5 | Setting
5.3 | Testing
5.3.1 | Create test plan
5.3.2 | Create checklist
5.3.3 | Create unit test case
5.3.4 | Create integration test case
5.3.5 | Excute integration test
5.3.6 | Excute system test
6 | Monitoring and Controlling
7 | Closing
7.1 | Create final report
7.2 | Postmortem

## WBS-Dic
Work Breakdown Structure Dictionary |  | Created by | LongNB, TuyenPT, DuongQT
|  | Reviewed by | DatQT
Work name | Dictionary
1. Initiate Project | The act of starting this project.
1.1 Kick-off Meeting | A meeting in which not only introduce the information of the project for team member but also brainstorm to improve the project.
1.2 Study necessary technique | Study all technique which need for project: Android, SQLite …
1.3Study feasibility | Study about the feasibility of project: main users, function …
1.4 Create report | Note all things we have done on a report.
2. Project Plan Phrase
2.1 Setup Project Environment | Install and set up the environment needed for developing the application.
2.1.1 Prepare Hardware | Prepare all equipment which need for project: laptop, android phone …
2.1.2 Setup develop tools | Install and set up the develop tools in which we are going to code this app.
2.2 Develop Project Schedule
2.2.1 Build WBS | Build work break down structure
2.2.2 Define project Estimate | Estimate all project
2.2.3 Define project Schedule plan | Create project schedule plan
3. Software Requirement Phase
3.1 User requirement specification | Create user requirement specification.
3.2 System requirement specification | Create system requirement specification.
3.3 Entity relationship diagram and data structure | Create relationship diagram and data structure
4. Design Description Phase | Create software design description to tell software what the program must do
4.1 System Architecture Design | To handle objects called “system”, in a way that supports reasoning about the structural properties of these objects
4.2 Component Diagram | Show the dependencies and interactions between software components
4.3 Sequence Diagram | Shows how processes operate with one another and in what order
4.4 User Interface Design | Design interaction between user and software application
4.5 Database Design and Data structure | Create database design to know database structure and relationship between tables
5. Implement Phrase
5.1 Build Data
5.1.1 Build sentence | Build all of sentences which application use for conversation function
5.1.2 Build sound file | Build sound files of sentences which application use for conversation function
5.2 Coding
5.2.1 Conversation | Include simple conversation sentences in many fields of life
5.2.2 Favorite | User can mark sentences which usually use
5.2.3 History | Show sentences which user used
5.2.4 Search | Develop seach function
5.2.5 Setting | Include checking version, voice play sensor settings, today’s talk notification settings…
5.3 Testing
5.3.1 Create test plan | How do the application tested, who will do the testing and how do bugs reported
5.3.2 Create checklist | List is mostly equivalent to Test plan, it will cover all quality assurance and testing standards
5.3.3 Create unit test case | Create unit test case to test each individual component to ensure that it is as defect-free as possible
5.3.4 Create integration test case | Occurs between unit and system testing to test functionally grouped components. It ensures a subset(s) of the entire system works together
5.3.5 Execute integration test | Which individual software modules are combined and tested as a group
5.3.6 Execute system test | Prepare environment for system testing
6. Monitoring and Controlling | Consists of those processes required to track, review, and orchestrate the progress and performance of a project; identify any areas in which changes to the plan are required; and initiate the corresponding changes
7. Closing
7.1 Create final report | Create final report to summary project result
7.2 Postmortem | Members review all project, what we did, advantages and disadvantages